## Sheet1
with land price
290000
| Total house price | 682943 | 972943
| Bank to lend | 614600
| total price including variation | 807688 | 1097688
Variation adjustments
date | total price to deposit (10%) | 68343
| Total amound adjustment/variation | 124745
| TOTAL SUM of changes | 193088
| Total amount Paid | 114652.34
| Total owing | 78435.66
2013-07-22 | inititial | 8000
2015-01-27 | deposit | 30000
2015-07-13 | pp2 | 40573
2015-08-19 | var 9-10-11 | 10632
2015-09-22 | var 12-13-14-15 a | 12723.67
| var 12-13-14-15 b | 12723.67
46309.34
progress
|  |  | Progress paid | 46309.34
Variations
2015-02-02 | 1-Geotech report | 300 | paid | 300
2015-02-12 | 4-Insulation | 230 | paid | 530 | 830
2015-06-30 | 5 - garage store room | 8400 | paid | 8930
2015-07-02 | 6-Ducting A/C, | 3800 | paid | 12730
2015-07-02 | 7-alfresco brick and window/linen | 3300 | paid | 16030
2015-07-02 | 8-remove balcony top of porch | -5800 | credit | 10230 | 9700
2015-07-14 | 9-appliance selection | 4057 | paid | 14287
2015-07-14 | 10-excavation add on | 2260 | paid | 16547
2015-07-15 | 11-PC Item | 4315 | paid | 20862 | 10632 | august
2015-07-16 | 12-alfresco wall | 930 | paid | 21792 | 38171
2015-07-20 | 13-plumbing to pantry | 860 | paid | 22652
2015-07-21 | 14-SolarWS | 3800 | paid | 26452
2015-08-19 | 15-kitchen | 32581 |  | 59033 | 12723.6667 | sept-oct-nov
2015-07-21 | 16-powder room modification | 340 |  | 59373 | 30430
2015-07-21 | 17-stage 1 tiling | 581 |  | 59954
2015-07-21 | 18-stage 2 tiling | 29509 |  | 89463 | 10143.3333 | dec-jan-feb
2015-07-24 | 19-walkin wardrobe | 300 |  | 89763 | 35582
| 20-electrical | 17076 |  | 106839
| 21-carpet | 10000 |  | 116839
| 22-privacy screen | 950 |  | 117789
2015-08-25 | 23-Alfresco Plumbing Provisions | 650 |  | 118439
| 24-Credit Piers | -384 |  | 118055
| 25-stairs upgrade | 6990 |  | 125045 | 11860.6667 | mar-april-May
| Air conditioning | 16000
| Alfresco | 9020 | deposit | 903
| owing to pay | 0 | 2nd | 1860
|  |  | final | 6257

## Sheet2
total-upgrades | 86562 | 21300 | 120000
solar |  | 3800
carpet | 10000
appliance option 2 | 4057
tiles | 30000
PC items | 4315
AirConditioning |  | 17500
fireplace |  |  | 15000
Swim SPA |  |  | 30000
kitchen | 35000
add-on excavation | 2260
alfresco wall | 930
Landscaping (front) |  |  | 25000
Landscaping(back) |  |  | 50000